PREDICTIVE CONSTRUCTION
PROJECT OVERRUN MODEL

Early-Warning Classification and Regression
for Cost Overruns and Schedule Delays

Project code: IP-DA-003
Sponsor: In Project LLC
Analyst: Narciso M. Dickson, PMP®

Synthetic-data disclosure: All project records and model outcomes are fictional. Model performance is not an industry benchmark, and production use on real construction projects is not authorized by this portfolio project.

# Contents

1. Executive Summary

2. Business Problem and Portfolio Progression

3. Analytical Lifecycle and Governance

4. Dataset, Feature Lineage, and Quality

5. Modeling Methodology

6. Classification Performance

7. Regression, Calibration, and Temporal Generalization

8. Feature Drivers and Project Risk Scoring

9. Dashboards and Portfolio Communication

10. Act Plan, Human Review, and Monitoring

11. Limitations, Responsible AI, and Conclusion

12. Sources and Deliverables

# 1. Executive Summary

This case study is the third project in a construction analytics portfolio. It combines the cost and schedule controls developed in Project 1 with the RFI and change-workflow indicators developed in Project 2 to predict future cost overruns and schedule delays from early and mid-project snapshots.

| Dataset | Cost model | Schedule model | Test risk bands |
| --- | --- | --- | --- |
| 2,362 clean projects 1,577 train 349 validation 436 test | Random Forest ROC-AUC 0.899 PR-AUC 0.774 | Logistic Regression ROC-AUC 0.756 PR-AUC 0.524 | 188 Red 138 Yellow 110 Green |

## Principal conclusions

Cost-overrun classification generalized strongly to the future synthetic test period.

Schedule-delay performance decreased from validation to test, creating a real model-monitoring concern rather than a result to hide.

CPI and current cost variance were the strongest cost-overrun predictors.

SPI, planned completion, procurement delay, and overdue workflow indicators were important schedule predictors.

Predictions were converted into Red, Yellow, and Green review priorities, but every score requires human review.

The Act phase defines a controlled-pilot path; it does not authorize production use.

# 2. Business Problem and Portfolio Progression

## Primary business question

Which early and mid-project indicators best predict material construction cost overruns and schedule delays, and how can management prioritize intervention before the outcomes become unavoidable?

## Portfolio progression

| Project | Title | Contribution |
| --- | --- | --- |
| Project 1 | Construction Project Controls Analytics | CPI, SPI, cost, schedule, contingency, EAC, and early-warning controls |
| Project 2 | Construction Change Order and RFI Analytics | RFI response, change approval, pending exposure, revision loops, and forecast lag |
| Project 3 | Predictive Construction Project Overrun Model | Time-validated probability and magnitude prediction with governance |

Project 3 uses a new independent synthetic dataset. It references feature concepts from Projects 1 and 2 without mixing their folders, repositories, or records.

# 3. Analytical Lifecycle and Governance

| Phase | CRISP-DM | DMAIC | Microsoft | PMI governance |
| --- | --- | --- | --- | --- |
| Ask | Business Understanding | Define | Business Understanding | Initiating / Planning |
| Prepare | Data Understanding | Measure | Data Acquisition and Understanding | Planning |
| Process | Data Preparation | Measure / early Analyze | Data Acquisition and Understanding | Executing / Monitoring |
| Analyze | Modeling and Evaluation | Analyze | Modeling | Executing / Monitoring |
| Share | Evaluation | Analyze / improvement design | Customer Acceptance | Stakeholder engagement |
| Act | Deployment | Improve and Control | Deployment / Acceptance | Executing / Monitoring / Closing |

The frameworks are conceptually aligned but are not treated as identical. The workflow is iterative, and quality or governance findings may require returning to earlier phases.

# 4. Dataset, Feature Lineage, and Quality

The deterministic generator created 2,400 intended projects with snapshots between approximately 35% and 60% planned completion. Raw tables intentionally contained duplicates, category variants, missing critical values, invalid numeric values, invalid dates, target inconsistencies, and orphan relationships.

| Control | Result |
| --- | --- |
| Raw project rows | 2,412 |
| Raw workflow rows | 2,417 |
| Raw outcome rows | 2,416 |
| Duplicate removals | 36 |
| Quarantined records | 123 |
| Clean model rows | 2,362 |
| Cleaning actions | 199 |
| SQLite integrity | ok |
| Foreign-key violations | 0 |

## Feature families

Project and contract attributes

CPI, SPI, cost variance, schedule variance, contingency, and productivity

Procurement, weather, and safety indicators

RFI response, overdue rates, revisions, reopening, and RFI-to-change conversion

Approved and pending change exposure, approval cycle, old pending rate, and forecast incorporation lag

Workflow handoffs, revision loops, and snapshot workflow-risk score

Final outcomes, final CPI/SPI, actual end date, final EAC, and final status were excluded from predictor matrices.

# 5. Modeling Methodology

| Element | Method |
| --- | --- |
| Time split | Train 2019–2023; Validation 2024; Test 2025 |
| Cost classification | Final cost overrun ≥10% |
| Schedule classification | Final schedule delay ≥30 days |
| Cost regression | Final cost-overrun percentage |
| Schedule regression | Final schedule-delay days |
| Classification candidates | Logistic Regression and Random Forest |
| Regression candidates | Ridge Regression and Random Forest Regressor |
| Champion selection | Validation PR-AUC for classification; validation MAE for regression |
| Threshold selection | Maximum validation F1; test untouched |
| Explainability | Permutation importance on held-out test data |

The model uses 40 predictors: 31 numeric and 9 categorical. Numeric fields are standardized for linear models, and categorical values are one-hot encoded with unknown-category handling.

# 6. Classification Performance

| Target | Champion | ROC-AUC | PR-AUC | Precision | Recall | F1 | Brier |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cost overrun | Random Forest | 0.899 | 0.774 | 0.625 | 0.811 | 0.706 | 0.123 |
| Schedule delay | Logistic Regression | 0.756 | 0.524 | 0.520 | 0.453 | 0.484 | 0.183 |

Figure 1. Classification, regression, and calibration performance.

# 7. Regression, Calibration, and Temporal Generalization

| Target | Model | MAE | RMSE | R² | Interpretation |
| --- | --- | --- | --- | --- | --- |
| Final_Cost_Overrun_Pct | Ridge Regression | 0.032 | 0.041 | 0.520 | Cost-overrun percentage points |
| Final_Cost_Overrun_Pct | Random Forest Regressor | 0.032 | 0.041 | 0.515 | Cost-overrun percentage points |
| Final_Schedule_Delay_Days | Ridge Regression | 15.528 | 19.499 | 0.294 | Schedule-delay days |
| Final_Schedule_Delay_Days | Random Forest Regressor | 15.403 | 18.953 | 0.333 | Schedule-delay days |

## Temporal degradation

The schedule classifier achieved validation ROC-AUC 0.856 but test ROC-AUC 0.756. The reduction suggests temporal variation in the synthetic portfolio. The result is retained as an example of why model performance must be monitored after deployment.

The monitoring demonstration produced a schedule probability PSI of 0.105, above the proposed Yellow threshold of 0.10.

# 8. Feature Drivers and Project Risk Scoring

| Rank | Cost feature | Importance | Schedule feature |
| --- | --- | --- | --- |
| 1 | CPI_Snapshot | 0.0502 | SPI_Snapshot |
| 2 | Cost_Variance_Pct_Snapshot | 0.0289 | Planned_Percent_Complete |
| 3 | Approved_Change_Value_Pct_Budget | 0.0080 | Procurement_Delay_Days_to_Date |
| 4 | Pending_Change_Exposure_Pct_Budget | 0.0030 | Overdue_RFI_Rate |
| 5 | Labor_Productivity_Index | 0.0026 | Old_Pending_Change_Rate |
| 6 | Contingency_Utilization_Pct | 0.0022 | Actual_Percent_Complete |
| 7 | Procurement_Delay_Days_to_Date | 0.0020 | RFI_On_Time_Rate |
| 8 | SPI_Snapshot | 0.0013 | Revision_Loop_Rate |
| 9 | Snapshot_Data_Completeness_Pct | 0.0012 | Complexity_Level |
| 10 | Complexity_Level | 0.0010 | Project_Type |

Feature importance measures predictive contribution under permutation. It does not establish that changing a feature will cause a better outcome.

## Top predicted-risk projects

| Project | Band | Overall | Cost | Schedule | Primary drivers |
| --- | --- | --- | --- | --- | --- |
| Gateway Bridge Program 1418 | Red | 99.8% | 94.0% | 97.4% | Slow change approval; Workflow risk score; Overdue RFI backlog |
| Granite Urban Village 1705 | Red | 99.8% | 89.1% | 97.7% | Overdue RFI backlog; Slow change approval; Workflow risk score |
| Horizon Neighborhood 34 | Red | 99.4% | 80.3% | 96.8% | Overdue RFI backlog; Workflow risk score; Slow RFI response |
| Redwood Logistics Center 1716 | Red | 99.2% | 91.6% | 90.9% | Overdue RFI backlog; Slow RFI response; Workflow risk score |
| Aspen Corporate Center 702 | Red | 99.1% | 91.8% | 89.2% | Overdue RFI backlog; Slow change approval; Slow RFI response |
| Northstar Highway Improvements 1925 | Red | 99.0% | 88.1% | 92.0% | Slow change approval; Workflow risk score; Slow RFI response |
| Pioneer Urban Village 1981 | Red | 98.8% | 94.1% | 80.4% | Overdue RFI backlog; Slow RFI response; Workflow risk score |

# 9. Dashboards and Portfolio Communication

The Share phase produced executive, model-performance, project-risk, and feature-driver dashboards plus Power BI and Tableau build specifications.

The communication design shows probability and risk band together, labels validation and test periods, and keeps synthetic-data, uncertainty, and human-review warnings visible.

# 10. Act Plan, Human Review, and Monitoring

## Controlled-pilot roadmap

Days 0–30: approve charter, prohibited uses, independent review, reproducibility, source mapping, and data-quality gates.

Days 31–60: conduct a silent pilot, train reviewers, and review thresholds and monitoring.

Days 61–90: conduct a limited visible pilot, record decisions and overrides, and make a formal go/no-go decision.

## Human review

Verify input data and snapshot context.

Review cost, schedule, and overall probabilities.

Review model and rule-based drivers.

Consider current project context and known events.

Accept, Override, Escalate, or Defer.

Assign an action, owner, due date, and evidence.

Record later outcomes for monitoring.

## Proposed monitoring

| Metric | Yellow | Red / stop |
| --- | --- | --- |
| Cost ROC-AUC | Yellow <0.82 | Red <0.78 |
| Schedule ROC-AUC | Yellow <0.75 | Red <0.70 |
| Probability PSI | Yellow >0.10 | Red >0.20 |
| Critical data quality | Any failure | Stop scoring |
| Segment AUC gap | Yellow >0.10 | Red >0.15 |
| Override rate | Yellow >30% | Red >50% |
| Model age | Review at 12 months | Mandatory decision at 18 months |

# 11. Limitations, Responsible AI, and Conclusion

All data is synthetic and may not represent real project distributions.

Performance is not an industry benchmark.

Target thresholds are case-study definitions.

Feature importance is predictive, not causal.

The schedule model shows temporal degradation.

Segment results have limited sample sizes.

Real deployment requires approved data, independent validation, calibration, drift review, human oversight, access controls, and incident response.

The model may not be used for contractual, legal, safety-critical, or personnel decisions.

## Conclusion

Project 3 completes a three-project construction analytics portfolio progression from descriptive project controls, to diagnostic workflow analytics, to predictive early warning. The project demonstrates technical modeling and business governance together, including the discipline to retain unfavorable temporal results and restrict unvalidated production use.

# 12. Sources and Deliverables

## Professional references

IBM CRISP-DM overview: https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=dm-crisp-help-overview

ASQ DMAIC: https://asq.org/quality-resources/dmaic

Microsoft Data Science Lifecycle: https://learn.microsoft.com/en-us/shows/dev-intro-to-data-science/what-is-the-data-science-lifecycle-2-of-28

PMI Process Groups: https://www.pmi.org/standards/process-groups

## Primary project deliverables

Analysis workbook and model-performance tables

Saved classification and regression pipelines

Feature manifest and model card

Executive and operational dashboards

Power BI and Tableau specifications

Batch scoring and model-monitoring scripts

Controlled-pilot Act plan, risk register, RACI, and override log

Complete Ask–Prepare–Process–Analyze–Share–Act documentation

End of Report